## Test_Cases
Features | Test Case ID | Test Case Description | Pre-Condition | Test Steps | Test Data | Expected Result | Actual Result | Status
Login Page | TC001 | Verify that the SauceDemo login page loads successfully | Browser is open and internet is available | 1. Open browser 2. Navigate to SauceDemo URL | URL:https://www.saucedemo.com/ | Login page loads successfully | AS EXPECTED | PASS
Login Page | TC002 | Verify that the SauceDemo logo is displayed | Login page is open | 1. Observe the login page 2. Locate the SauceDemo logo | URL:https://www.saucedemo.com/ | SauceDemo logo is clearly visible | AS EXPECTED | PASS
Login Page | TC003 | Verify the color, shape, size, and position of the SauceDemo logo | Login page is open | 1. Observe the logo 2. Compare it with the expected UI design | SauceDemo logo | Logo appearance and position match the expected design | AS EXPECTED | PASS
Login Page | TC004 | Verify that the Username field is displayed | Login page is open | 1. Locate the Username field | N/A | Username field is visible and accessible | AS EXPECTED | PASS
Login Page | TC005 | Verify that the Username field displays the expected placeholder | Login page is open | 1. Locate Username field 2. Check placeholder text | Expected Username placeholder | Correct placeholder is displayed | AS EXPECTED | PASS
Login Page | TC006 | Verify that the Password field is displayed | Login page is open | 1. Locate Password field | N/A | Password field is visible and accessible | AS EXPECTED | PASS
Login Page | TC007 | Verify that the Password field displays the expected placeholder | Login page is open | 1. Locate Password field 2. Check placeholder | Expected Password placeholder | Correct placeholder is displayed | AS EXPECTED | PASS
Login Page | TC008 | Verify that the Login button is displayed and enabled | Login page is open | 1. Locate Login button 2. Check its state | N/A | Login button is visible and enabled | AS EXPECTED | PASS
Login Page | TC009 | Verify that login page elements are properly aligned | Login page is open | 1. Observe all login elements 2. Check alignment and spacing | N/A | Elements are properly aligned without overlap | AS EXPECTED | PASS
Login Page | TC010 | Verify that password characters are masked | Login page is open | 1. Click Password field 2. Enter password | secret_sauce | Password is displayed as masked characters | AS EXPECTED | PASS
Login Page | TC011 | Verify login page compatibility across supported browsers | Supported browsers are installed | 1. Open SauceDemo in each supported browser 2. Observe login page | Chrome, Firefox, Edge, Safari | Login page displays and functions correctly in supported browsers | AS EXPECTED | PASS
Login Page | TC012 | Verify login page responsiveness | Login page is accessible | 1. Open page on desktop 2. Resize browser 3. Check smaller screen sizes | Desktop, tablet, mobile resolutions | Page adjusts correctly without broken layout | THE PAGE CONTENT IS NOT ADJUSTING | FAIL
Login Page | TC013 | Verify the login page title | Login page is open | 1. Check browser tab title | Expected SauceDemo title | Correct page title is displayed | AS EXPECTED | PASS
Login Page | TC014 | Verify login with valid credentials | Login page is open | 1. Enter valid Username 2. Enter valid Password 3. Click Login | standard_user / secret_sauce | User logs in successfully | AS EXPECTED | PASS
Login Page | TC015 | Verify URL changes after successful login | Login page is open | 1. Enter valid credentials 2. Click Login 3. Check URL | standard_user / secret_sauce | URL changes from login page to Inventory page URL | AS EXPECTED | PASS
Login Page | TC016 | Verify successful login redirects to Inventory page | Login page is open | 1. Enter valid credentials 2. Click Login | standard_user / secret_sauce | User is redirected to Inventory page | AS EXPECTED | PASS
Login Page | TC017 | Verify Inventory page loads after login | Valid login credentials are available | 1. Login successfully 2. Observe Inventory page | standard_user / secret_sauce | Inventory page loads successfully | AS EXPECTED | PASS
Login Page | TC018 | Verify authenticated session during navigation | User is logged in | 1. Login 2. Navigate between Inventory, Product Details and Cart | Valid user credentials | User remains authenticated during navigation | AS EXPECTED | PASS
Login Page | TC019 | Verify Enter key submits login form | Login page is open | 1. Enter Username 2. Enter Password 3. Press Enter | standard_user / secret_sauce | Login form is submitted and user reaches Inventory page | AS EXPECTED | PASS
Login Page | TC020 | Verify copy-paste credentials in login fields | Login page is open | 1. Copy Username 2. Paste into Username field 3. Copy Password 4. Paste into Password field | standard_user / secret_sauce | Credentials are accepted and login works successfully | AS EXPECTED | PASS
Login Page | TC021 | Verify login with both fields empty | Login page is open | 1. Leave both fields empty 2. Click Login | Blank Username and Password | Login is not successful | AS EXPECTED | PASS
Login Page | TC022 | Verify error message for empty fields | Login page is open | 1. Leave fields empty 2. Click Login | Blank fields | Appropriate validation error message is displayed | AS EXPECTED | PASS
Login Page | TC023 | Verify login without Username | Login page is open | 1. Leave Username empty 2. Enter Password 3. Click Login | Password: secret_sauce | Login fails | AS EXPECTED | PASS
Login Page | TC024 | Verify login without Password | Login page is open | 1. Enter Username 2. Leave Password empty 3. Click Login | Username: standard_user | Login fails | AS EXPECTED | PASS
Login Page | TC025 | Verify error message when Username is missing | Login page is open | 1. Leave Username empty 2. Enter Password 3. Click Login | / secret_sauce | Appropriate Username validation message is displayed | AS EXPECTED | PASS
Login Page | TC026 | Verify error message when Password is missing | Login page is open | 1. Enter Username 2. Leave Password empty 3. Click Login | standard_user / | Appropriate Password validation message is displayed | AS EXPECTED | PASS
Login Page | TC027 | Verify login with valid Username and invalid Password | Login page is open | 1. Enter valid Username 2. Enter invalid Password 3. Click Login | standard_user / invalid123 | Login fails and appropriate error is displayed | AS EXPECTED | PASS
Login Page | TC028 | Verify login with invalid Username and valid Password | Login page is open | 1. Enter invalid Username 2. Enter valid Password 3. Click Login | invalid_user / secret_sauce | Login fails and appropriate error is displayed | AS EXPECTED | PASS
Login Page | TC029 | Verify login with invalid Username and Password | Login page is open | 1. Enter invalid Username 2. Enter invalid Password 3. Click Login | invalid_user / invalid123 | Login fails and appropriate error is displayed | AS EXPECTED | PASS
Login Page | TC030 | Verify error for valid Username and invalid Password | Login page is open | 1. Enter valid Username 2. Enter invalid Password 3. Click Login | standard_user / wrongpass | Correct authentication error is displayed | AS EXPECTED | PASS
Login Page | TC031 | Verify error for invalid Username and valid Password | Login page is open | 1. Enter invalid Username 2. Enter valid Password 3. Click Login | wrong_user / secret_sauce | Correct authentication error is displayed | AS EXPECTED | PASS
Login Page | TC032 | Verify error for invalid Username and invalid Password | Login page is open | 1. Enter invalid Username 2. Enter invalid Password 3. Click Login | wrong_user / wrongpass | Correct authentication error is displayed | AS EXPECTED | PASS
Login Page | TC033 | Verify repeated unsuccessful login behavior | Login page is open | 1. Enter invalid credentials repeatedly 2. Submit each attempt | Invalid credentials | Application handles repeated failures according to defined security behavior | AS EXPECTED | PASS
Login Page | TC034 | Verify Username minimum and maximum character limits | Login page is open | 1. Enter values below minimum 2. Enter maximum allowed value 3. Enter value above maximum | Boundary Username values | Field follows defined character-limit rules | THE USERNAME FIELD IS TAKING UNLIMITED CHARACTER WITHOULD ANY ERROR MESSAGFES | FAIL
Login Page | TC035 | Verify Username handling of spaces | Login page is open | 1. Enter Username containing spaces 2. Submit | standard_user | Username should get rejected according to requirements | AS EXPECTED | PASS
Login Page | TC036 | Verify Username handling of special characters and numbers | Login page is open | 1. Enter Username containing numbers/special characters 2. Submit | user123, user@123 | Username should accept numbers and special characters and handle the input correctly | AS EXPECTED | PASS
Inventory | TC037 | Verify all available products are displayed after login | User is logged in | 1. Login 2. Open Inventory page 3. Count products | Valid credentials | All expected products are displayed | AS EXPECTED | PASS
Inventory | TC038 | Verify product names are visible | Inventory page is open | 1. Inspect each product card | Product list | Every product displays its name | AS EXPECTED | PASS
Inventory | TC039 | Verify product images are visible | Inventory page is open | 1. Inspect product cards | Product images | Every product displays its image | AS EXPECTED | PASS
Inventory | TC040 | Verify product descriptions are visible | Inventory page is open | 1. Inspect product information | Product descriptions | Product descriptions are displayed correctly | AS EXPECTED | PASS
Inventory | TC041 | Verify product prices are visible | Inventory page is open | 1. Inspect product cards | Product prices | Every product displays a price | AS EXPECTED | PASS
Inventory | TC042 | Verify every product has Add to Cart button | Inventory page is open | 1. Inspect all product cards | Product list | Every product has an Add to Cart button | AS EXPECTED | PASS
Inventory | TC043 | Verify products load within expected time | User is logged in | 1. Open Inventory page 2. Observe loading time | Normal network | Products load within defined threshold | AS EXPECTED | PASS
Inventory | TC044 | Verify product data alignment | Inventory page is open | 1. Inspect names, images, descriptions, prices and buttons | Product list | Product information is properly aligned | AS EXPECTED | PASS
Inventory | TC045 | Verify there are no broken product images | Inventory page is open | 1. Inspect all product images | Product images | All images load successfully | AS EXPECTED | PASS
Inventory | TC046 | Verify duplicate products are not displayed | Inventory page is open | 1. Review product list 2. Compare product names/details | Product list | No unintended duplicate products are displayed | AS EXPECTED | PASS
Inventory | TC047 | Verify sorting dropdown is visible | Inventory page is open | 1. Locate sorting dropdown | Sort dropdown | Dropdown is visible and usable | AS EXPECTED | PASS
Inventory | TC048 | Verify sorting by Name A-Z | Inventory page is open | 1. Open dropdown 2. Select Name A-Z | Name A-Z | Products are sorted alphabetically from A to Z | AS EXPECTED | PASS
Inventory | TC049 | Verify sorting by Name Z-A | Inventory page is open | 1. Open dropdown 2. Select Name Z-A | Name Z-A | Products are sorted alphabetically from Z to A | AS EXPECTED | PASS
Inventory | TC050 | Verify sorting by Price Low to High | Inventory page is open | 1. Open dropdown 2. Select Price Low to High | Price Low to High | Products are sorted from lowest to highest price | AS EXPECTED | PASS
Inventory | TC051 | Verify sorting by Price High to Low | Inventory page is open | 1. Open dropdown 2. Select Price High to Low | Price High to Low | Products are sorted from highest to lowest price | AS EXPECTED | PASS
Inventory | TC052 | Verify sorting behavior after page refresh | Inventory page is open | 1. Apply sorting 2. Refresh page 3. Observe product order | Name A-Z | Sorting behaves according to expected application behavior | AS EXPECTED | PASS
Inventory | TC053 | Verify sorting after adding products to cart | Inventory page is open | 1. Add product 2. Apply sorting | Product + sort option | Sorting works correctly without losing cart state | AS EXPECTED | PASS
Inventory | TC054 | Verify sorting dropdown alignment | Inventory page is open | 1. Inspect dropdown position and spacing | Sort dropdown | Dropdown is properly aligned | AS EXPECTED | PASS
Inventory | TC055 | Verify adding a single product to cart | Inventory page is open | 1. Select one product 2. Click Add to Cart | Any product | Selected product is added to cart | AS EXPECTED | PASS
Inventory | TC056 | Verify adding multiple products | Inventory page is open | 1. Select multiple products 2. Click Add to Cart for each | Multiple products | All selected products are added | AS EXPECTED | PASS
Inventory | TC057 | Verify Add to Cart changes to Remove | Product is displayed | 1. Click Add to Cart | Any product | Button changes to Remove | AS EXPECTED | PASS
Inventory | TC058 | Verify cart count increases after adding product | Inventory page is open | 1. Add one product 2. Observe cart badge | One product | Cart badge increases by one | AS EXPECTED | PASS
Inventory | TC059 | Verify correct product is added | Inventory page is open | 1. Add a specific product 2. Open cart | Selected product | Correct selected product appears in cart | AS EXPECTED | PASS
Inventory | TC060 | Verify same product cannot be added twice | Inventory page is open | 1. Add product 2. Attempt to add same product again | One product | Product is not duplicated in cart | AS EXPECTED | PASS
Inventory | TC061 | Verify cart state after Inventory page refresh | Product is already added | 1. Refresh Inventory page 2. Check product/cart state | Added product | Cart items and count remain unchanged after refresh. | AS EXPECTED | PASS
Inventory | TC062 | Verify cart badge count accuracy | Products are available | 1. Add multiple products 2. Compare products with badge count | 2–3 products | Badge count matches number of added products | AS EXPECTED | PASS
Inventory | TC063 | Verify Add/Remove button responsiveness | Inventory page is open | 1. Click Add to Cart 2. Click Remove | Product | Button responds immediately and correctly | AS EXPECTED | PASS
Inventory | TC064 | Verify Remove button removes product | Product is in cart | 1. Click Remove | Added product | Product is removed from cart | AS EXPECTED | PASS
Inventory | TC065 | Verify cart count decreases after removal | Product is in cart | 1. Note badge count 2. Remove one product | Multiple products | Badge count decreases by one | AS EXPECTED | PASS
Inventory | TC066 | Verify removed product disappears from cart | Product is added | 1. Remove product 2. Open cart | Added product | Removed product is not displayed in cart | AS EXPECTED | PASS
Inventory | TC067 | Verify removing all products resets cart | Multiple products are added | 1. Remove every product | Multiple products | Cart becomes empty and badge is cleared | AS EXPECTED | PASS
Inventory | TC068 | Verify Remove changes back to Add to Cart | Product is added | 1. Click Remove | Added product | Button changes back to Add to Cart | AS EXPECTED | PASS
Inventory | TC069 | Verify remove functionality from Inventory page | Product is added | 1. Click Remove on Inventory page | Added product | Product is removed successfully | AS EXPECTED | PASS
Inventory | TC070 | Verify product name opens details page | Inventory page is open | 1. Click product name | Any product | Corresponding Product Details page opens | AS EXPECTED | PASS
Inventory | TC071 | Verify product image opens details page | Inventory page is open | 1. Click product image | Any product | Corresponding Product Details page opens | AS EXPECTED | PASS
Inventory | TC072 | Verify browser Back button | Product Details page is open | 1. Click browser Back | N/A | User returns to previous Inventory page | AS EXPECTED | PASS
Inventory | TC073 | Verify Inventory page URL | User is logged in | 1. Open Inventory page 2. Check URL | https://www.saucedemo.com/inventory.html | Correct Inventory URL is displayed | AS EXPECTED | PASS
Product Details | TC074 | Verify Product Details page opens correctly | User is logged in | 1. Click a product name | Any product | Product Details page opens successfully | AS EXPECTED | PASS
Product Details | TC075 | Verify correct product details are displayed | Product Details page is open | 1. Compare displayed product with selected product | Selected product | Correct product information is displayed | AS EXPECTED | PASS
Product Details | TC076 | Verify product image quality | Product Details page is open | 1. Inspect product image | Product image | Image is clear and properly displayed | AS EXPECTED | PASS
Product Details | TC077 | Verify product title accuracy | Product Details page is open | 1. Compare title with Inventory page | Selected product | Title matches the selected product | AS EXPECTED | PASS
Product Details | TC078 | Verify product price accuracy | Product Details page is open | 1. Compare price with Inventory page | Selected product | Price matches Inventory page | AS EXPECTED | PASS
Product Details | TC079 | Verify product description accuracy | Product Details page is open | 1. Compare description | Selected product | Description is accurate and consistent | AS EXPECTED | PASS
Product Details | TC080 | Verify Add to Cart functionality | Product Details page is open | 1. Click Add to Cart | Selected product | Product is added to cart | AS EXPECTED | PASS
Product Details | TC081 | Verify Remove functionality | Product is added from details page | 1. Click Remove | Selected product | Product is removed from cart | AS EXPECTED | PASS
Product Details | TC082 | Verify cart badge update | Product Details page is open | 1. Add product 2. Observe cart badge | Selected product | Cart badge updates correctly | AS EXPECTED | PASS
Product Details | TC083 | Verify Back to Products button | Product Details page is open | 1. Locate 2. Click Back to Products | N/A | Button is visible and functional | AS EXPECTED | PASS
Product Details | TC084 | Verify navigation back to Inventory | Product Details page is open | 1. Click Back to Products | N/A | User returns to Inventory page | AS EXPECTED | PASS
Product Details | TC085 | Verify direct Product Details URL access | User is authenticated | 1. Enter valid product URL directly | Valid product URL | Product Details page opens correctly | AS EXPECTED | PASS
Product Details | TC086 | Verify no UI overlap on Product Details page | Product Details page is open | 1. Inspect page at supported resolutions | Desktop/mobile | No UI elements overlap | AS EXPECTED | PASS
Product Details | TC087 | Verify responsive Product Details page | Product Details page is open | 1. Resize browser 2. Inspect layout | Mobile/tablet/desktop | Page remains usable and properly aligned | AS EXPECTED | PASS
Product Details | TC088 | Verify Product Details page load speed | User is logged in | 1. Open product details 2. Measure loading time | Normal network | Page loads within defined threshold | AS EXPECTED | PASS
Product Details | TC089 | Verify Product Details state after refresh | Product Details page is open | 1. Add product 2. Refresh page | Selected product | Expected product/cart state is retained | AS EXPECTED | PASS
Product Details | TC090 | Verify browser Back/Forward navigation | Product Details page is open | 1. Navigate Back 2. Navigate Forward | N/A | Browser navigation works correctly | AS EXPECTED | PASS
Product Details | TC091 | Verify product details consistency | Product is visible on Inventory page | 1. Note product details 2. Open details page 3. Compare | Selected product | Product information matches across pages | AS EXPECTED | PASS
Cart | TC092 | Verify cart icon is visible | User is logged in | 1. Open Inventory page 2. Locate cart icon | N/A | Cart icon is visible | AS EXPECTED | PASS
Cart | TC093 | Verify cart icon opens Cart page | User is logged in | 1. Click cart icon | N/A | Cart page opens | AS EXPECTED | PASS
Cart | TC094 | Verify added products appear in cart | Products are added | 1. Open Cart page | Added products | Added products are displayed | AS EXPECTED | PASS
Cart | TC095 | Verify product quantity | Products are added | 1. Open cart 2. Check quantities | Added products | Quantity is displayed correctly | AS EXPECTED | PASS
Cart | TC096 | Verify product price in cart | Product is added | 1. Open cart 2. Check price | Selected product | Correct price is displayed | AS EXPECTED | PASS
Cart | TC097 | Verify product details in cart | Product is added | 1. Open cart 2. Compare details | Selected product | Product information is correct | AS EXPECTED | PASS
Cart | TC098 | Verify multiple items display correctly | Multiple products are added | 1. Open Cart | Multiple products | All selected products are displayed correctly | AS EXPECTED | PASS
Cart | TC099 | Verify cart data consistency | Products are added | 1. Compare Inventory and Cart information | Selected products | Cart information matches Inventory information | AS EXPECTED | PASS
Cart | TC100 | Verify all items can be removed | Multiple products are in cart | 1. Remove each product | Multiple products | All products are removed | AS EXPECTED | PASS
Cart | TC101 | Verify empty cart behavior | Cart is empty | 1. Open Cart page | Empty cart | Correct empty-cart state is displayed | AS EXPECTED | PASS
Cart | TC102 | Verify Continue Shopping button | Cart page is open | 1. Click Continue Shopping | N/A | User returns to Inventory page | AS EXPECTED | PASS
Cart | TC103 | Verify Checkout button | Cart contains product | 1. Click Checkout | Added product | Checkout Information page opens | AS EXPECTED | PASS
Cart | TC104 | Verify checkout behavior with empty cart | Cart is empty | 1. Attempt to access checkout | Empty cart | It should return an error message and couldn’t access the chectout page | The checkout button I giving the acces of the checkout page with empty cart | FAIL
Cart | TC105 | Verify Cart page responsiveness | Cart page is open | 1. Resize browser 2. Inspect page | Mobile/tablet/desktop | Cart remains usable and properly aligned | AS EXPECTED | PASS
Cart | TC106 | Verify Cart page layout | Cart page is open | 1. Inspect all elements | N/A | No broken or overlapping layouts are present | AS EXPECTED | PASS
Cart | TC107 | Verify Cart page buttons are clickable | Cart page is open | 1. Click available buttons | N/A | Buttons respond correctly | AS EXPECTED | PASS
Cart | TC108 | Verify Cart page load speed | User is logged in | 1. Open Cart page 2. Observe load time | Normal network | Cart page loads within defined threshold | AS EXPECTED | PASS
Cart | TC109 | Verify cart behavior after refresh | Product is in cart | 1. Refresh Cart page | Added product | Cart state behaves according to expected application behavior | AS EXPECTED | PASS
Cart | TC110 | Verify session persistence on Cart page | User is logged in | 1. Navigate through Cart | Valid session | User remains authenticated | AS EXPECTED | PASS
Checkout | TC111 | Verify First Name field visibility in checkout page | User is on Checkout Information page | 1. Locate First Name field | N/A | First Name field is visible | AS EXPECTED | PASS
Checkout | TC112 | Verify Last Name field visibility in checkout page | Checkout page is open | 1. Locate Last Name field | N/A | Last Name field is visible | AS EXPECTED | PASS
Checkout | TC113 | Verify Postal Code field visibility in checkout page | Checkout page is open | 1. Locate Postal Code field | N/A | Postal Code field is visible | AS EXPECTED | PASS
Checkout | TC114 | Verify Continue button visibility | Checkout page is open | 1. Locate Continue button | N/A | Continue button is visible and enabled | AS EXPECTED | PASS
Checkout | TC115 | Verify Cancel button functionality | Checkout page is open | 1. Click Cancel | N/A | User returns to the previous shopping page | AS EXPECTED | PASS
Checkout | TC116 | Verify mandatory field validation | Checkout page is open | 1. Leave required fields empty 2. Click Continue | Blank fields | Required fields are validated | AS EXPECTED | PASS
Checkout | TC117 | Verify error for empty First Name | Checkout page is open | 1. Leave First Name empty 2. Fill other fields 3. Click Continue | First Name blank | Appropriate error is displayed | AS EXPECTED | PASS
Checkout | TC118 | Verify error for empty Last Name | Checkout page is open | 1. Leave Last Name empty 2. Fill other fields 3. Click Continue | Last Name blank | Appropriate error is displayed | AS EXPECTED | PASS
Checkout | TC119 | Verify error for empty Postal Code | Checkout page is open | 1. Leave Postal Code empty 2. Fill other fields 3. Click Continue | Postal Code blank | Appropriate error is displayed | AS EXPECTED | PASS
Checkout | TC120 | Verify special-character handling | Checkout page is open | 1. Enter special characters 2. Submit | @#$% | Input is handled according to validation rules | AS EXPECTED | PASS
Checkout | TC121 | Verify numeric input handling | Checkout page is open | 1. Enter numeric values in fields | 12345 | Numeric input is accepted/rejected according to field rules | AS EXPECTED | PASS
Checkout | TC122 | Verify maximum character limits | Checkout page is open | 1. Enter values at and beyond maximum limit | Boundary values | Field enforces defined maximum limit | The maximum limit is being not defined | FAIL
Checkout | TC123 | Verify spaces-only input validation | Checkout page is open | 1. Enter spaces in required field 2. Click Continue | " " | User should not be allowed to continue. A validation message should be displayed indicating that the First Name field is required. | the input filed is not showing error and getting continued | FAIL
Checkout | TC124 | Verify checkout with valid information | Cart contains products | 1. Enter valid details 2. Click Continue | John / Doe / 411001 | User should proceed to the Overview page and successfully complete the order. The Order Confirmation page should be displayed. | AS EXPECTED | PASS
Checkout | TC125 | Verify all selected products appear in checkout | Products are in cart | 1. Proceed to Checkout Overview | Selected products | All selected products are displayed | AS EXPECTED | PASS
Checkout | TC126 | Verify product quantities on checkout | Products are in cart | 1. Open Checkout Overview 2. Check quantities | Selected products | Correct quantities are displayed | AS EXPECTED | PASS
Checkout | TC127 | Verify subtotal calculation | Products are selected | 1. Note product prices 2. Compare displayed subtotal | Product prices | Subtotal equals sum of selected product prices | AS EXPECTED | PASS
Checkout | TC128 | Verify tax calculation | Checkout Overview is open | 1. Calculate expected tax 2. Compare displayed tax | Product subtotal | Displayed tax is calculated correctly | AS EXPECTED | PASS
Checkout | TC129 | Verify total amount calculation | Checkout Overview is open | 1. Add subtotal and tax 2. Compare total | Subtotal + Tax | Total equals subtotal plus tax | AS EXPECTED | PASS
Checkout | TC130 | Verify Finish button visibility | Checkout Overview is open | 1. Locate Finish button | N/A | Finish button is visible and enabled | AS EXPECTED | PASS
Checkout | TC131 | Verify Cancel button functionality on Overview | Checkout Overview is open | 1. Click Cancel | N/A | User should be redirected to the Inventory page and the checkout process should be cancelled. | AS EXPECTED | PASS
Checkout | TC132 | Verify order completion message | Valid checkout data is entered | 1. Click Finish | Valid order | Appropriate order completion message is displayed | AS EXPECTED | PASS
Checkout | TC133 | Verify confirmation page | Order is completed | 1. Observe confirmation page | Completed order | Confirmation page displays correct information | AS EXPECTED | PASS
Checkout | TC134 | Verify Back Home button | Order confirmation page is open | 1. Click Back Home | N/A | User returns to Inventory page | AS EXPECTED | PASS
Checkout | TC135 | Verify cart resets after order completion | Order is completed | 1. Complete order 2. Open cart | Completed order | Cart is empty after successful order | AS EXPECTED | PASS
Checkout | TC136 | Verify post-checkout redirection | Order is completed | 1. Click Finish 2. Observe URL/page | Valid order | User is redirected to expected confirmation page | AS EXPECTED | PASS
Checkout | TC137 | Verify duplicate order prevention | Valid order information is entered | 1. Complete order 2. Attempt repeated submission | Valid order | Duplicate order is not created | AS EXPECTED | PASS
Checkout | TC138 | Verify session handling after checkout | User has completed order | 1. Navigate after checkout | Valid session | Session behaves according to expected application rules | AS EXPECTED | PASS
Checkout | TC139 | Verify checkout cannot continue with invalid data | Checkout page is open | 1. Enter invalid data 2. Click Continue | Invalid checkout data | User cannot proceed and validation errors are displayed | User is able to do ckeckout with both valid and invalid data | FAIL
Checkout | TC140 | Verify browser refresh during checkout | User is on checkout page | 1. Refresh page 2. Observe state | Checkout data | Application handles refresh according to expected behavior | AS EXPECTED | PASS
Checkout | TC141 | Verify browser Back navigation during checkout | User is on checkout page | 1. Click browser Back | N/A | User is returned to the appropriate previous page | AS EXPECTED | PASS
Menu | TC142 | Verify hamburger menu visibility | User is logged in | 1. Open supported page 2. Locate menu icon | N/A | Hamburger menu icon is visible | AS EXPECTED | PASS
Menu | TC143 | Verify hamburger menu opens on click | User is logged in | 1. Click menu icon | N/A | Navigation menu opens | AS EXPECTED | PASS
Menu | TC144 | Verify hamburger menu closes correctly | Menu is open | 1. Click menu close control | N/A | Menu closes successfully | AS EXPECTED | PASS
Menu | TC145 | Verify all menu options are visible | Menu is open | 1. Inspect menu items | Expected menu options | All expected options are displayed | AS EXPECTED | PASS
Menu | TC146 | Verify About link functionality | Menu is open | 1. Click About | About link | Correct About page opens | AS EXPECTED | PASS
Menu | TC147 | Verify Logout functionality | User is logged in | 1. Open menu 2. Click Logout | Logged-in user | User is logged out successfully | AS EXPECTED | PASS
Menu | TC148 | Verify Reset App State functionality | User has products in cart | 1. Open menu 2. Click Reset App State | Products in cart | Application state is reset | AS EXPECTED | pass
Menu | TC149 | Verify menu responsiveness | User is logged in | 1. Open menu on different screen sizes | Mobile/tablet/desktop | Menu displays correctly on supported sizes | AS EXPECTED | PASS
Menu | TC150 | Verify clicking outside closes menu | Menu is open | 1. Click outside menu | N/A | Menu closes if outside-click behavior is supported | MENU DOES NOT CLOSEES | FAIL
Menu | TC151 | Verify menu animation behavior | User is logged in | 1. Open menu 2. Close menu 3. Observe transition | N/A | Menu animation behaves as expected | AS EXPECTED | PASS
Menu | TC152 | Verify keyboard accessibility of menu | User is logged in | 1. Use Tab/keyboard navigation 2. Open menu 3. Navigate options | Keyboard | Menu and options are keyboard accessible | ITS NOT KEYBOARD ACCESSABLE | FAIL
Menu | TC153 | Verify unauthorized access after logout | User has logged out | 1. Attempt to access protected page | Protected URL | Unauthorized access is prevented according to application rules | AS EXPECTED | PASS
Menu | TC154 | Verify session ends after logout | User is logged in | 1. Click Logout 2. Attempt authenticated navigation | Logged-in user | User session is ended | AS EXPECTED | PASS
Menu | TC155 | Verify Reset App State removes cart items | Products are in cart | 1. Open menu 2. Click Reset App State 3. Open cart | Products in cart | Cart items are removed | AS EXPECTED | PASS
Menu | TC156 | Verify navigation links are correct | Menu is open | 1. Click each navigation option | Menu links | Each link opens the correct destination | AS EXPECTED | PASS
Footer | TC157 | Verify footer visibility | Supported page is open | 1. Scroll to bottom | N/A | Footer is visible | AS EXPECTED | PASS
Footer | TC158 | Verify footer position consistency | Supported pages are available | 1. Open multiple pages 2. Inspect footer | Multiple pages | Footer position is consistent | AS EXPECTED | PASS
Footer | TC159 | Verify Twitter/X link functionality | Footer is visible | 1. Click Twitter/X link | Twitter/X link | Correct destination opens | AS EXPECTED | PASS
Footer | TC160 | Verify Facebook link functionality | Footer is visible | 1. Click Facebook link | Facebook link | Correct destination opens | AS EXPECTED | PASS
Footer | TC161 | Verify LinkedIn link functionality | Footer is visible | 1. Click LinkedIn link | LinkedIn link | Correct destination opens | AS EXPECTED | PASS
Footer | TC162 | Verify social links open correct pages | Footer is visible | 1. Click each social link 2. Verify destination | Social links | Each link opens the expected destination | AS EXPECTED | PASS
Footer | TC163 | Verify social links open in new tab when required | Footer is visible | 1. Click social link 2. Observe browser behavior | Social links | Link opens in new tab when required | AS EXPECTED | PASS
Footer | TC164 | Verify social links are not broken | Footer is visible | 1. Open each social link | Social links | Links do not lead to broken pages | AS EXPECTED | PASS
Footer | TC165 | Verify footer text | Footer is visible | 1. Read footer text 2. Compare with expected content | Expected footer text | Footer text is correct | AS EXPECTED | PASS
Footer | TC166 | Verify footer responsiveness | Footer is visible | 1. Resize browser 2. Inspect footer | Mobile/tablet/desktop | Footer remains responsive | AS EXPECTED | PASS
Footer | TC167 | Verify footer alignment | Footer is visible | 1. Inspect footer elements | N/A | Footer elements are properly aligned | AS EXPECTED | PASS
Footer | TC168 | Verify footer visibility across pages | Multiple pages are available | 1. Open each supported page 2. Check footer | Application pages | Footer appears consistently where expected | AS EXPECTED | PASS
Performance | TC169 | Verify application page load time | Browser and internet are available | 1. Open application pages 2. Measure load time | Normal network | Pages load within defined performance threshold | AS EXPECTED | PASS
Performance | TC170 | Verify Inventory page performance | User is logged in | 1. Open Inventory page 2. Measure load time | Normal network | Inventory page loads within threshold | AS EXPECTED | PASS
Performance | TC171 | Verify Cart page performance | Product is in cart | 1. Open Cart 2. Measure load time | Normal network | Cart page loads within threshold | AS EXPECTED | PASS
Performance | TC172 | Verify Checkout page performance | Product is in cart | 1. Navigate to Checkout 2. Measure load time | Normal network | Checkout page loads within threshold | AS EXPECTED | PASS
Performance | TC173 | Verify responsiveness after multiple actions | User is logged in | 1. Sort products 2. Add items 3. Open cart 4. Navigate pages | Multiple actions | Application remains responsive without noticeable lag | AS EXPECTED | PASS
Performance | TC174 | Verify product image loading speed | Inventory page is open | 1. Observe product image loading | Product images | Images load within defined threshold | AS EXPECTED | PASS
Performance | TC175 | Verify sorting performance | Inventory page is open | 1. Select different sort options repeatedly | Sort options | Sorting completes without noticeable lag | AS EXPECTED | PASS
Performance | TC176 | Verify cart update performance | Inventory page is open | 1. Add products 2. Remove products repeatedly | Multiple products | Cart updates occur without noticeable lag | AS EXPECTED | PASS
UI | TC177 | Verify font consistency | Application is accessible | 1. Navigate through pages 2. Compare fonts | Application pages | Fonts are consistent throughout the application | AS EXPECTED | PASS
UI | TC178 | Verify button alignment | Application page is open | 1. Inspect buttons across pages | Application buttons | Buttons are properly aligned | AS EXPECTED | PASS
UI | TC179 | Verify product image alignment | Inventory page is open | 1. Inspect product images | Product images | Images are properly aligned | AS EXPECTED | PASS
UI | TC180 | Verify responsive design on mobile | Application is accessible | 1. Open application on mobile resolution 2. Navigate pages | Mobile resolution | Application remains usable and properly aligned | AS EXPECTED | PASS
UI | TC181 | Verify responsive design on tablet | Application is accessible | 1. Open application at tablet resolution 2. Navigate pages | Tablet resolution | Application remains usable and properly aligned | AS EXPECTED | PASS
UI | TC182 | Verify responsive design on desktop | Application is accessible | 1. Open application at desktop resolution 2. Navigate pages | Desktop resolution | Application displays correctly | AS EXPECTED | PASS
UI | TC183 | Verify browser compatibility | Supported browsers are installed | 1. Open application in supported browsers 2. Navigate through key flows | Chrome, Firefox, Edge, Safari | Application works correctly across supported browsers | AS EXPECTED | PASS
UI | TC184 | Verify scrollbar behavior | Application page is open | 1. Scroll page vertically/horizontally where applicable | Different screen sizes | Scrollbars behave correctly without unwanted overflow | AS EXPECTED | PASS
UI | TC185 | Verify text readability | Application page is open | 1. Inspect text across pages | Application text | Text is readable and does not overlap other elements | AS EXPECTED | PASS
UI | TC186 | Verify color consistency | Application pages are open | 1. Compare colors of common UI components | UI colors | Colors are consistent with expected design | AS EXPECTED | PASS
UI | TC187 | Verify hover effects | Application page is open | 1. Move cursor over interactive elements | Buttons/links | Expected hover effects are displayed | AS EXPECTED | PASS
UI | TC188 | Verify spacing between clickable elements | Application page is open | 1. Inspect buttons, links and controls | Interactive elements | Adequate spacing is maintained between elements | AS EXPECTED | PASS
UI | TC189 | Verify no overlapping UI elements | Application is accessible | 1. Navigate through pages 2. Test different screen sizes | Mobile/tablet/desktop | No elements overlap or become inaccessible | AS EXPECTED | PASS
UI | TC190 | Verify overall UI consistency across pages | Application is accessible | 1. Navigate through Login, Inventory, Details, Cart and Checkout pages 2. Compare common UI components | Application pages | UI design, fonts, colors, spacing and controls remain consistent | AS EXPECTED | PASS